## Basic Info
Team Name | BadGirls
Repository | https://github.com/stackoverjoe/SpaceHunt
Online | http://web.cecs.pdx.edu/~jml27/
See other tabs of this sheets for more information

## Commits by Week
Number of Commits this Week
Name | 2019-11-05 | 2019-11-12 | 2019-11-19 | 2019-11-26 | 2019-12-03 | Total
Maggie Haddon | 0 | 1 | 4 | 2 | 4 | 11
Joeseph Leland | 0 | 16 | 5 | 2 | 3 | 26
James Fotheringham | 2 | 9 | 0 | 6 | 2 | 19
Travis Kamerer | 0 | 25 | 0 | 0 | 5 | 30
Jasmine Callon | 1 | 7 | 3 | 2 | 3 | 16
^ automatic, you can double-check with https://github.com/stackoverjoe/SpaceHunt/graphs/contributors
https://github.com/stackoverjoe/SpaceHunt/graphs/contributors

## User Stories
User Story | Status | Contributors (and their roles) | Accossiated Files
1 | Done-Done | Joe - Code/design, Maggie some code/research | Map.js, spaceMap.html
2 | Did Not Pass Review | James - Design (HTML/CSS), Jasmine - Code, Design Fixes | options.html; options.css; options.js; readLocalStorage.js
3 | Done-Done | Travis - Code/design | Map.js, spaceMap.html
4 | Done-Done | Travis - Code/design | Map.js, spaceMap.html
5 | Not Started | James - Design (HTML/CSS), Jasmine - Code, Design Fixes | options.html; options.css; options.js; readLocalStorage.js
6 | Done-Done | Maggie - Code/design
7 | Did Not Pass Review | Maggie - Code
8 | Done-Done | Maggie - Code/design
9 | In Progress | Jasmine - Code | saveGame.js, loadGame.js, readLocalStorage.js
10 | Done-Done | James - Code/Design | map.js; spaceMap.html
11 | Done-Done | James - Code/Design | map.js; spaceMap.html; blackjack.js
12 | Not Started
13 | Not Started
14 | Not Started
15 | Not Started
16 | Not Started
17 | Not Started
18 | Not Started
19 | Done-Done | Travis - Code/Design | Map.js, spaceMap.html